KIDS GAMES APP - 6 WEEK ROADMAP

Repo based plan (review date: February 25, 2026)

REPO DERIVED STARTING POINT

- Current shipped game loops: Math Adventure, Alphabet Fun, Animal Memory.

- Core progression exists in code: 20 levels, star based unlocks, daily goal, streak + shield, milestone themes, recovery mode.

- Parent and profile features exist: onboarding, achievements popup, journey popup, parent weekly report from activity log.

- Persistence architecture is local first: one centralized Zustand store persisted via AsyncStorage (`app-store`).

- Quality baseline exists: 25 tests passing across progression, scoring, achievements, profile, session flow, parent report.

- Current implementation gaps visible in repo:

- `app/settings.tsx` has placeholder handlers for Music/Sounds buttons.

- Home settings popup has Reset button without implementation.

- `src/services/` is empty, so no sync/back-end boundary exists yet.

- README architecture notes are partly stale vs current store/persistence reality.

MILESTONES

- Milestone 1 (Weeks 1-2): Reliability and architecture alignment.

- Milestone 2 (Weeks 3-4): Parent trust and learning quality.

- Milestone 3 (Weeks 5-6): Sync ready foundation and release hardening.

WEEK BY WEEK TABLE

| Week | Weekly Goal | Clear Deliverables |

| --- | --- | --- |

| Week 1 | Remove known UX debt in settings and align docs with real architecture. | 1) Implement working Music/Sounds/Reset actions across settings flows. 2) Decide and standardize one settings entry path (home popup vs `/settings` screen). 3) Update README to reflect AsyncStorage and current folder reality. 4) Add tests for settings and reset behavior. |

| Week 2 | Harden gameplay session reliability and add observability baseline. | 1) Audit `lastSession` resume/expiry behavior for all 3 games. 2) Add regression tests for restore edge cases (expired session, level mismatch, post-result clear). 3) Add analytics interface behind `ENABLE_ANALYTICS` without external dependency. 4) Ship reliability checklist used as PR gate. |

| Week 3 | Strengthen parent workflow with trust controls and clearer insights. | 1) Add parent gate protection (PIN or equivalent) before Parent Progress. 2) Improve weekly report messaging and trend clarity. 3) Add acceptance checks for parent readability and actionability. 4) Add tests for parent gate and report edge cases. |

| Week 4 | Activate localization plumbing and tune learning progression. | 1) Introduce string dictionary and wire `settings.language` to real UI text (home + at least 1 full game flow). 2) Tune progression/scoring thresholds using playtest feedback while preserving test invariants. 3) Add tests for translated labels and progression safety bounds. 4) Publish a balancing change log. |

| Week 5 | Create service boundaries so app can remain local first but sync ready. | 1) Add typed contracts under `src/services` for profile/progress/report snapshots. 2) Build optional offline queue + retry contract. 3) Define local/remote merge policy for progression data. 4) Document failure paths and fallback behavior. |

| Week 6 | Produce release candidate and ship readiness evidence. | 1) Run full verification (`npm test`, `npm run lint`, `npm run typecheck`). 2) Validate gameplay on compact devices and performance sensitive screens. 3) Produce EAS preview + production Android builds. 4) Publish go/no-go checklist with owners for any open issues. |

DEPENDENCIES (EXPLICIT)

- Product decision needed by Week 3 for parent gate UX, reset policy, and parent unlock fallback.

- Localization support needed by Week 4 for Spanish copy quality and review process.

- QA device access needed (small-height and lower-performance Android devices).

- Sync strategy decision needed by Week 4: local-only this cycle or minimal backend contracts in Week 5.

- Refactor bandwidth needed to safely evolve `useAppStore.ts` without destabilizing all game flows.

RISKS (EXPLICIT)

- Risk: Centralized store changes can regress many features at once.

Mitigation: Add contract tests before refactors and enforce test/lint/typecheck gates.

- Risk: AsyncStorage payload may grow (session payloads + activity logs).

Mitigation: Monitor payload size, trim aggressively, avoid unnecessary persisted fields.

- Risk: Audio stack churn (`expo-av` deprecation warning already present).

Mitigation: Isolate audio adapter and evaluate migration path early.

- Risk: Scope creep from trying to do backend + analytics + gameplay polish together.

Mitigation: Keep Week 5 sync interfaces optional and preserve offline-first default.

- Risk: Timeline slip due animation-heavy UI and responsive branches.

Mitigation: Prioritize behavioral completeness before visual polish.

DEFINITION OF DONE (END OF WEEK 6)

- All three game loops remain stable with resume/progression/result flows validated.

- Parent flow is protected and produces useful weekly recommendations.

- Language setting changes visible strings in prioritized surfaces.

- Service boundaries exist for future sync without breaking local gameplay.

- Release checklist, build artifacts, and ownership are documented.